CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Hanoi, August 2019 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 20/09/2026 | A | HungVD | Add 1.2 , 1.3 |
| 20/9/2026 | A | AnNT | Add 1.1 |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Dekiru Curriculum & Learning Progress |  | 9 |
| 1.1 | Display curriculum roadmap based on Dekiru Nihongo | Simple | 5 |
| 1.2 | Learning progress tracking | Simple | 4 |
| 2 | Skill Practice Hub (Per Lesson) |  | 60 |
| 2.1 | Interactive listening practice | Medium | 6 |
| 2.2 | Pronunciation practice (Shadowing & Phoneme analysis) | Complex | 10 |
| 2.3 | Scenario-based AI roleplay | Complex | 9 |
| 2.4 | Interactive reading comprehension & Quick lookup | Medium | 6 |
| 2.5 | Kanji writing & Memorization (Stroke order & Mnemonics) | Medium | 6 |
| 2.6 | Interactive grammar learning | Simple | 5 |
| 2.7 | Spaced repetition flashcard review (SRS Algorithm) | Complex | 10 |
| 2.8 | Review quizzes & Performance assessment summary | Medium | 8 |
| 3 | AI Engine & Language Processing |  | 38 |
| 3.1 | Interactive conversational video & Subtitle streaming | Medium | 8 |
| 3.2 | Context-aware voice chatbot (LLM & TTS) | Complex | 16 |
| 3.3 | Pronunciation assessment & In-depth grammar error correction | Complex | 14 |
| 4 | Gamification |  | 28 |
| 4.1 | Educational mini-games (Word matching, Speed challenge) | Medium | 9 |
| 4.2 | Reward & Achievement system (EXP, Coins) | Simple | 6 |
| 4.3 | Learning streak management system | Simple | 6 |
| 4.4 | Leaderboard | Medium | 7 |
| 5 | Administration & System (Admin / CMS) |  | 42 |
| 5.1 | Authentication & Role-Based Access Control (RBAC) | Medium | 8 |
| 5.2 | Student & Class management | Simple | 6 |
| 5.3 | Dekiru course content management system (CMS) | Complex | 12 |
| 5.4 | Question bank & Exam management | Medium | 8 |
| 5.5 | Statistical reporting & Learning analytics | Medium | 8 |
| Total Estimated Effort (man-days) |  |  | 177 |

### 1.2 Project Objectives

- Enhance Knowledge of Modern Technologies: Master modern software technologies, including Spring Boot, React, MySQL, and integrated AI models for natural language processing and speech recognition.

- Provide a Specialized Educational Solution: Develop a high-quality web-based Japanese learning application specifically designed around the Dekiru Nihongo textbook, helping FPTU Software Engineering students overcome learning barriers, master vocabulary, grammar, and kanji, and improve their speaking and reading skills for university examinations.

- Implement AI-Based Personalized Learning: Apply AI algorithms to analyze each student's learning weaknesses, automatically recommend suitable exercise sets, and provide interactive tools for practicing speaking and reading comprehension.

- Strengthen Communication and Teamwork: Improve collaboration efficiency through daily stand-up meetings, phased progress reporting, task management on GitHub, and close coordination among BA, Developer, and Tester roles.

- Apply Software Engineering Standards and Practices: Follow the Agile Scrum development methodology, establish rigorous testing processes, and maintain standardized documentation throughout the software development life cycle.

Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% | 50 | 40% | Conduct code and functionality reviews before merging code. |
| 2 | Unit Test | 95% | 20 | 10% | Test the backend code using JaCoCo and verify business logic. |
| 3 | Integration Test | 95% | 10 | 5% | Verify the integration between the Backend and Frontend, database connectivity, and external services. |
| 4 | System Test | 95% | 5 | 5% | Perform end-to-end testing of the website's main functionalities. |
| 5 | Acceptance Test | 95% | 5 | 5% | Conduct the final evaluation and verification, and obtain approval from the supervising lecturer. |

Milestone Timeliness (%):

Allocated Effort (man-days):

]

### 1.3 Project Risks

[List out the details on project risks in the table below]

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Internal conflicts | High | Medium | Hold weekly team meetings to establish and align on the working process. If conflicts cannot be resolved, seek advice from the supervising lecturer. |
| 2 | Lack of experience and technical skills among team members | High | High | Appoint a Tech Lead to guide team members on the required technologies. Team members are also expected to proactively research and self-study technologies such as Spring Boot and React. |
| 3 | Data loss | Low | High | For documentation: Store files on Google Drive and restore them from backups when necessary. For code: Restore previous versions using the project's commit history on GitHub. |
| 4 | Code merge conflicts | High | High | Create a separate branch for each module. After completing a module, merge the code into the main development branch. In case of conflicts, conduct a code review to identify and resolve the issues. |
| 5 | Limited project development time | High | High | Evaluate and prioritize the completion of the project's core features. Move advanced features to the backlog for future development. |

## 2. Management Approach

To ensure the successful implementation and timely delivery of the project, the team adopts Scrum framework. This approach allows the team to be adaptive to changes, maintain continuous communication, and deliver incremental functionality through short iterations (Sprints). Project progress, tasks, and issues will be tracked transparently using tools such as GitHub Projects. Daily stand-ups, lanning, review, and retrospective meetings are conducted regularly to maintain alignment and continuous improvement.

### 2.1 Project Process

The project applies the Scrum development process model, organized into 7 Sprints (2 weeks per Sprint) across a 14-week lifecycle:

- Sprint 0 (Weeks 1 – 2): Project Initialization & Training

  - Finalize Software Requirements Specification (SRS) and architecture design.

  - Conduct team training on Spring Boot, React, and Git workflows.

  - Initialize project repositories, CI/CD pipelines, and base database schemas.

- Sprint 1 (Weeks 3 – 4): Core Authentication & Lesson CMS

  - Implement User/Admin Authentication & Authorization (Spring Security + JWT).

  - Build Admin Dashboard for Lesson CMS and video upload modules.

- Sprint 2 (Weeks 5 – 6): Dekiru Curriculum & Media Streaming

  - Develop Student Lesson View, Kanji stroke canvas (HanziWriter), and Grammar detail screens.

  - Implement video streaming and interactive transcript/audio player.

- Sprint 3 (Weeks 7 – 8): AI Integration (Speech & Pronunciation Assistance)

  - Integrate Whisper STT and Gemini Flash API.

  - Implement voice recording and AI-driven pronunciation error analysis & feedback (non-grading).

- Sprint 4 (Weeks 9 – 10): Gamification & Mini-games

  - Develop Kanji Battle (radical matching) and Grammar Quest mini-games.

  - Implement Streak system, EXP progression, and real-time Leaderboards.

- Sprint 5 (Weeks 11 – 12): System Integration & Performance Optimization

  - End-to-end integration testing between Spring Boot, React, and Gemini AI.

  - Caching implementation (Redis) and database query optimization.

  - Comprehensive defect fixing and UI/UX polishing.

- Sprint 6 (Weeks 13 – 14): Final Deployment, Acceptance Testing

  - Conduct User Acceptance Testing (UAT) and Security/Load testing.

  - Finalize all technical documentation, user guides, and slide presentations for defense.

### 2.2 Quality Management

To achieve high quality and meet the software requirements, the team applies the following quality assurance strategies:

- Defect Prevention:

  - Define clear Definition of Done (DoD) and Definition of Ready (DoR) for all tasks.

  - Establish consistent coding conventions, project architecture rules, and static code analysis (e.g., using SonarQube).

- Reviewing:

  - Code Review: Every feature branch must be reviewed and approved via Pull Requests by at least one peer/lead before merging into the main branch.

  - Design & Documentation Review: Review database schemas, API contracts (OpenAPI), and UI/UX wireframes before actual implementation.

- Unit Testing:

  - Developers are responsible for writing automated unit tests (e.g., JUnit, Mockito for Spring Boot; Jest for frontend) covering core business logic and critical utility functions, aiming for at least 86% code coverage.

- Integration Testing:

  - Verify the interaction between different layers (Controller - Service - Repository) and test end-to-end API communication using tools like Postman or Spring Boot Test.

- System Testing:

  - QA/Testers perform functional, UI, and scenario-based testing on a staging environment to ensure the whole system satisfies all functional and non-functional requirements prior to release.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Java Spring Boot | Backend Developers | Sprint 0 (Week 1), 5 days (2 hours/day) | Mandatory |
| Git, Github | All Team Members | Sprint 0 (Week 1), 2 days (1.5 hours/day) | Mandatory |
| React.js | Frontend Developers | Sprint 0 (Week 1–2), 4 days (2 hours/day) | Have ≥ 6 months hands-on React experience |
| AI Integration | AI / Backend Lead | Sprint 0 (Week 2), 3 days (2 hours/day) | Prior experience integrating LLM APIs |
| Database Design (MySQL) & API Conventions (REST/OpenAPI) | All Developers | Sprint 0 (Week 2), 2 days (2 hours/day) | Mandatory |

## 3. Project Deliverables

[Given the main project deliverables. Those can be internal and/or external deliverables. Students can prepare master schedule like the table format as below or in the more detailed structure as the sample in the attached sample file - Report2_Sample High Level Project Schedule.pdf]

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 – Project Introduction | Week 1 | Project introduction, problem, opportunity, and scope |
| 2 | Report 2 – Project Plan v0.9 | Week 2 | Initial project plan |
| 3 | Report 3 – SRS v0.9 + Project Plan v1.0 | Week 3 | Software requirements and updated project plan |
| 4 | Report 4 – SDS v0.9 + Project Plan v1.1 | Week 4–5 | Software design document and updated project plan |
| 5 | Software Package 1 | Week 6–7 | Software version after Iteration 1 |
| 6 | Software Package 2 | Week 8–9 | Software version after Iteration 2 |
| 7 | Software Package 3 | Week 10–11 | Software version after Iteration 3 |
| 8 | Report 5 – Test Report | Week 11 | Software testing results |
| 9 | Full Software Package | Week 13 | Complete software package after testing and bug fixing |
| 10 | Report 6 – User Guide | Week 14 | User guide for the system |
| 11 | Report 7 – Final Project Report | Week 14 | Final project documentation |

## 4. Responsibility Assignments

RACI Chart: R~Responsible, A~Accountable, C~Consulted, I~Informed

| Responsibility | HungVDHE18 1369 | TuHAHE1821 11 | ThuNTMHE180 810 | AnNTHE1731 89 | LinhPMHE18 7215 |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | R,A | R | C | C | I |
| Project Introduction | A | C | R | I | C |
| Requirements Analysis & SRS | R,A | R | C | R | R |
| UI/UX Design | R | R | R,A | R | C |
| System Architecture Design | R,A | R | C | R | R |
| Database Design | R,A | R | R | R | C |
| Front-end Development | A | C | C | R | R |
| Back-end & API Development | R,A | R | R | C | C |
| AI Integration | R | R | C | R,A | C |
| System Integration | A,R | R | R | R | R |
| Integration Testing | R | A,R | C | R | R |
| System Testing & Bug Fixing | C | A,R | C | R | R |
| Deployment & Configuration | A,R | R | R | R | R |
| Project Documentation & Final Report | R | R | R,A | R | R |
| Final Presentation & Demo | A,R | R | R | R | R |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Team Meeting | All members | Discuss project progress, tasks, and problems | Weekly | Google Meet / Face-to- face |
| Task Progress Update | All members | Track task completion and assign new tasks | 2–3 times/ week | GitHub / Zalo |
| Document Sharing | All members | Share and update project documents | As needed | Google Drive / Google Docs |
| Code Review | All members | Review source code and identify technical problems | When code is updated | Google Meet/ GitHub |
| Project Review | All members | Review project status and prepare deliverables | End of each stage | Google Meet / Face-to- face |

## 6. Configuration Management

### 6.1 Document Management

Management Tools:

- Google Drive

- Google Docs

- Google Sheets

- GitHub

### The team uses Google Drive to store and manage project documents such as the Project Introduction, SRS, design documents, testing documents, reports, and presentation slides.

### Google Docs and Google Sheets are used for collaborative editing and updating project information. GitHub is also used to store and manage technical documents related to the project, helping the team track changes and maintain document versions.

### The Project Manager is responsible for monitoring progress, consolidating documents, and reviewing the final versions before submission to the mentor.

### 6.2 Source Code Management

Management Tools:

- GitHub

The team uses GitHub to manage and store the project source code, including the Front-end, Back-end, API, Database, and AI integration components.

Each team member works on a separate branch corresponding to their assigned tasks, then commits and pushes the code to the repository. Once a feature is completed, the code is reviewed and merged into the main branch to ensure system stability.

The Project Manager is responsible for monitoring the repository, managing source code integration, and preparing a stable version for testing, deployment, and demonstration.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Java/SpringBoot (BackEnd), React (Frontend) |
| Database | MySQL |
| IDEs/Editors | Visual Studio Code, IntelliJ |
| Diagramming | DrawIO, Figma, Visual Paragram |
| Documentation | Ms Office, Google Docs/Sheets |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Vercel(Front-end), Railway(Back-end, MySQL) |
| Project management | Jira(Schedule, Tasks, Defects) |
| Test tools | Postman |