CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Hanoi, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 20/09/2026 | A | HungVD | Add 1.2 , 1.3 |
| 20/9/2026 | A | AnNT | Add 1.1 |
| 20/09/2026 | A | TuHA | Add 4, 6.1, 6.2, 6.3 |
| 20/09/2026 | A | LinhPM | Add 3, 5 |
| 20/09/2026 | A | ThuNTM | Add 2.1, 2.2, 2.3 |
| 25/09/2026 | M | ThuNTM | Fix 2.1 |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Project Initiation |  | ### 4 |
| 1.1 | Complete the Project Introduction report | Medium | ### 4 |
| 2 | Project Planning |  | ### 11 |
| 2.1 | Prepare the Project Management Plan | Medium | ### 5 |
| 2.2 | Prepare and maintain the project schedule | Simple | ### 2 |
| 2.3 | Update weekly and project tracking reports | Medium | ### 4 |
| 3 | Software Development |  | ### 289 |
| 3.1 | Analysis and Design |  | ### 21 |
| 3.1.1 | Complete the Software Requirements Specification | Complex | ### 6 |
| 3.1.2 | Complete the Software Design Document | Complex | ### 5 |
| 3.1.3 | Design the application and database | Complex | ### 5 |
| 3.1.4 | Set up shared platform services | Medium | ### 3 |
| 3.1.5 | Assess and optimize system capacity | Medium | ### 2 |
| 3.2 | Iteration 1 / Platform and Learning Materials |  | ### 92 |
| 3.2.1 | Accounts and Student Approval |  | ### 18 |
| 3.2.1.1 | Register and verify accounts | Medium | ### 1 |
| 3.2.1.2 | Sign in and manage sessions | Complex | ### 7 |
| 3.2.1.3 | Manage roles and access control | Complex | ### 4 |
| 3.2.1.4 | Review and approve student accounts | Complex | ### 3 |
| 3.2.1.5 | Update account information and status | Medium | ### 2 |
| 3.2.1.6 | Send notifications to students | Medium | ### 1 |
| 3.2.2 | Curriculum and Learning Progress |  | ### 25 |
| 3.2.2.1 | View the learning roadmap and lessons | Medium | ### 7 |
| 3.2.2.2 | View lesson details | Simple | ### 1 |
| 3.2.2.3 | Resume an in-progress lesson | Simple | ### 1 |
| 3.2.2.4 | View lesson and course progress | Medium | ### 3 |
| 3.2.2.5 | Save and restore learning progress | Medium | ### 4 |
| 3.2.2.6 | Play lesson videos | Medium | ### 6 |
| 3.2.2.7 | View synchronized video subtitles | Medium | ### 2 |
| 3.2.2.8 | Resume video playback | Medium | ### 1 |
| 3.2.3 | Learning Materials and Basic Practice |  | ### 49 |
| 3.2.3.1 | Read lessons with pronunciation aids | Simple | ### 3 |
| 3.2.3.2 | Answer reading comprehension questions | Simple | ### 2 |
| 3.2.3.3 | View Kanji information and stroke order | Simple | ### 3 |
| 3.2.3.4 | Learn Kanji with mnemonic aids | Simple | ### 1 |
| 3.2.3.5 | Track Kanji review status | Medium | ### 5 |
| 3.2.3.6 | Complete grammar exercises | Medium | ### 5 |
| 3.2.3.7 | View and interact with flashcards | Simple | ### 6 |
| 3.2.3.8 | Open lesson-based flashcard decks | Simple | ### 2 |
| 3.2.3.9 | Mark and save memorization status | Medium | ### 3 |
| 3.2.3.10 | Manage the curriculum structure | Medium | ### 4 |
| 3.2.3.11 | Author lesson content | Medium | ### 4 |
| 3.2.3.12 | Manage images, audio, and subtitles | Medium | ### 8 |
| 3.2.3.13 | Preview and publish lessons | Complex | ### 3 |
| 3.3 | Iteration 2 / Core AI, Skills Practice, and Assessment |  | ### 101 |
| 3.3.1 | Core AI: Assessment, Conversation, and Personalization |  | ### 64 |
| 3.3.1.1 | AI pronunciation assessment | Complex | ### 7 |
| 3.3.1.2 | AI suggestions for natural expression (Gemini scope to confirm) | Complex | ### 9 |
| 3.3.1.3 | Practice scenario-based conversations with AI | Complex | ### 6 |
| 3.3.1.4 | View hints and translations in AI conversations | Simple | ### 2 |
| 3.3.1.5 | View AI conversation results | Medium | ### 2 |
| 3.3.1.6 | View grammar error explanations (AI scope to confirm) | Complex | ### 2 |
| 3.3.1.7 | Analyze results and recommend review content | Medium | ### 2 |
| 3.3.1.8 | Establish AI conversation sessions | Complex | ### 10 |
| 3.3.1.9 | Stream real-time audio to and from AI | Complex | ### 11 |
| 3.3.1.10 | Adapt AI responses to conversation context | Complex | ### 6 |
| 3.3.1.11 | Secure, store, and monitor AI sessions | Complex | ### 7 |
| 3.3.2 | Listening and Recording Practice |  |  |
| 3.3.2.1 | Play and control listening practice content | Medium | ### 22 |
| 3.3.2.2 | Complete listening exercises and view results | Medium | ### 8 |
| 3.3.2.3 | Record and replay spoken practice | Medium | ### 3 |
| 3.3.3 | Tests and Question Bank |  | ### 11 |
| 3.3.3.1 | Start and take tests | Medium | ### 15 |
| 3.3.3.2 | Submit tests and receive scores | Complex | ### 2 |
| 3.3.3.3 | Manage the question bank | Medium | ### 5 |
| 3.3.3.4 | Create and edit questions | Medium | ### 4 |
| 3.3.3.5 | Configure test blueprints | Medium | ### 3 |
| 3.4 | Iteration 3 / Learning Motivation and Finalization |  | ### 1 |
| 3.4.1 | Games, Rewards, and Leaderboards |  | ### 58 |
| 3.4.1.1 | Play the word matching game | Simple | ### 34 |
| 3.4.1.2 | Play the speed challenge | Medium | ### 3 |
| 3.4.1.3 | View game scores and rewards | Medium | ### 3 |
| 3.4.1.4 | View game instructions and assistance | Simple | ### 4 |
| 3.4.1.5 | Earn points and reward coins | Medium | ### 3 |
| 3.4.1.6 | Redeem rewards | Medium | ### 3 |
| 3.4.1.7 | View personal achievements | Simple | ### 1 |
| 3.4.1.8 | View and maintain learning streaks | Medium | ### 1 |
| 3.4.1.9 | Freeze and restore streaks | Medium | ### 6 |
| 3.4.1.10 | Receive study reminders | Medium | ### 1 |
| 3.4.1.11 | Calculate learning rankings | Medium | ### 1 |
| 3.4.1.12 | View personal and peer rankings | Simple | ### 6 |
| 3.4.2 | User Feedback |  | ### 2 |
| 3.4.2.1 | Submit ratings and feedback | Medium | ### 10 |
| 3.4.2.2 | Review and handle feedback | Medium | ### 6 |
| 3.4.2.3 | Export feedback data | Simple | ### 3 |
| 3.4.3 | Deployment and System Monitoring |  | ### 1 |
| 3.4.3.1 | Package and deploy the application | Complex | ### 14 |
| 3.4.3.2 | Back up and restore data | Complex | ### 10 |
| 3.4.3.3 | Monitor operations and send alerts | Medium | ### 2 |
| 3.5 | System Testing |  | ### 2 |
| 3.5.1 | Plan system tests | Simple | ### 17 |
| 3.5.2 | Test functionality and usability | Medium | ### 1 |
| 3.5.3 | Test information security | Medium | ### 7 |
| 3.5.4 | Complete test documentation and reports | Medium | ### 4 |
| 4 | Transition and Handover |  | ### 5 |
| 4.1 | Prepare software user guides | Simple | ### 14 |
| 4.2 | Complete the final project report | Medium | ### 3 |
| 4.3 | Prepare and present project results | Simple | ### 5 |
| 4.4 | Address feedback and hand over the product | Medium | ### 2 |
| 4.5 | Prepare the operations guide | Simple | ### 3 |
| 5 | Project Closing |  | ### 1 |
| 5.1 | Rehearse the presentation and defense | Medium | ### 7 |
| 5.2 | Submit required reports and source code | Simple | ### 5 |
| 5.3 | Present and defend the project | Simple | ### 1 |
| Total Estimated Effort (man-days) |  |  | 325 |

### 1.2 Project Objectives

- Enhance Knowledge of Modern Technologies: Master modern software technologies, including Spring Boot, React, MySQL, and integrated AI models for natural language processing and speech recognition.

- Provide a Specialized Educational Solution: Develop a high-quality web-based Japanese learning application specifically designed around the Dekiru Nihongo textbook, helping FPTU Software Engineering students overcome learning barriers, master vocabulary, grammar, and kanji, and improve their speaking and reading skills for university examinations.

- Implement AI-Based Personalized Learning: Apply AI algorithms to analyze each student's learning weaknesses, automatically recommend suitable exercise sets, and provide interactive tools for practicing speaking and reading comprehension.

- Strengthen Communication and Teamwork: Improve collaboration efficiency through daily stand-up meetings, phased progress reporting, task management on GitHub, and close coordination among BA, Developer, and Tester roles.

- Apply Software Engineering Standards and Practices: Follow the Agile Scrum development methodology, establish rigorous testing processes, and maintain standardized documentation throughout the software development life cycle.

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% | 50 | 40% | Conduct code and functionality reviews before merging code. |
| 2 | Unit Test | 95% | 20 | 10% | Test the backend code using JaCoCo and verify business logic. |
| 3 | Integration Test | 95% | 10 | 5% | Verify the integration between the Backend and Frontend, database connectivity, and external services. |
| 4 | System Test | 95% | 5 | 5% | Perform end-to-end testing of the website's main functionalities. |
| 5 | Acceptance Test | 95% | 5 | 5% | Conduct the final evaluation and verification, and obtain approval from the supervising lecturer. |

### 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Internal conflicts | High | Medium | Hold weekly team meetings to establish and align on the working process. If conflicts cannot be resolved, seek advice from the supervising lecturer. |
| 2 | Lack of experience and technical skills among team members | High | High | Appoint a Tech Lead to guide team members on the required technologies. Team members are also expected to proactively research and self-study technologies such as Spring Boot and React. |
| 3 | Data loss | Low | High | For documentation: Store files on Google Drive and restore them from backups when necessary. For code: Restore previous versions using the project's commit history on GitHub. |
| 4 | Code merge conflicts | High | High | Create a separate branch for each module. After completing a module, merge the code into the main development branch. In case of conflicts, conduct a code review to identify and resolve the issues. |
| 5 | Limited project development time | High | High | Evaluate and prioritize the completion of the project's core features. Move advanced features to the backlog for future development. |

## 2. Management Approach

To ensure the successful implementation and timely delivery of the project, the team adopts an iterative development approach. This approach enables the team to adapt to changing requirements, maintain continuous communication among team members, and gradually develop and improve the system through short development iterations.

Project progress, tasks, and issues are managed and tracked transparently using GitHub Projects. During each iteration, the team conducts planning, regular progress meetings, reviews, and retrospectives to coordinate tasks, monitor progress, evaluate completed functionality, identify issues, and continuously improve the development process.

### 2.1 Project Process (Iterative Development Process)

The lifecycle is partitioned into fixed-length, timeboxed iterations (2 weeks each). Every iteration executes a complete micro-lifecycle:

- Iteration Planning: Select high-priority, dependency-aligned user stories from the product backlog.

- Analysis & Detailed Design: Update SRS specifications and design targeted DB schemas/API endpoints for the iteration scope.

- Implementation: Write production code alongside automated unit tests.

- Testing & Integration: Execute unit tests, integration tests, and automated regression suites against the cumulative codebase.

- Iteration Review & Retrospective: Demonstrate the working executable build to advisors/stakeholders and refine team collaboration workflows.

### 2.2 Quality Management

To achieve high quality and meet the software requirements, the team applies the following quality assurance strategies:

- Defect Prevention:

  - Define clear Definition of Done (DoD) and Definition of Ready (DoR) for all tasks.

  - Establish consistent coding conventions, project architecture rules, and static code analysis (e.g., using SonarQube).

- Reviewing:

  - Code Review: Every feature branch must be reviewed and approved via Pull Requests by at least one peer/lead before merging into the main branch.

  - Design & Documentation Review: Review database schemas, API contracts (OpenAPI), and UI/UX wireframes before actual implementation.

- Unit Testing:

  - Developers are responsible for writing automated unit tests (e.g., JUnit, Mockito for Spring Boot; Jest for frontend) covering core business logic and critical utility functions, aiming for at least 86% code coverage.

- Integration Testing:

  - Verify the interaction between different layers (Controller - Service - Repository) and test end-to-end API communication using tools like Postman or Spring Boot Test.

- System Testing:

  - QA/Testers perform functional, UI, and scenario-based testing on a staging environment to ensure the whole system satisfies all functional and non-functional requirements prior to release.

### 2.3 Training Plan

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| Java Spring Boot | Backend Developers | Week 1, 5 days (2 hours/day) | Mandatory |
| Git, Github | All Team Members | Week 1, 2 days (1.5 hours/day) | Mandatory |
| React.js | Frontend Developers | Week 1–2, 4 days (2 hours/day) | Have ≥ 6 months hands-on React experience |
| AI Integration | AI / Backend Lead | Week 2, 3 days (2 hours/day) | Prior experience integrating LLM APIs |
| Database Design (MySQL) & API Conventions (REST/OpenAPI) | All Developers | Week 2, 2 days (2 hours/day) | Mandatory |

## 3. Project Deliverables

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 – Project Introduction | Week 1 | Project introduction, problem, opportunity, and scope |
| 2 | Report 2 – Project Plan v0.9 | Week 2 | Initial project plan |
| 3 | Report 3 – SRS v0.9 + Project Plan v1.0 | Week 3 | Software requirements and updated project plan |
| 4 | Report 4 – SDS v0.9 + Project Plan v1.1 | Week 4–5 | Software design document and updated project plan |
| 5 | Software Package 1 | Week 6–7 | Software version after Iteration 1 |
| 6 | Software Package 2 | Week 8–9 | Software version after Iteration 2 |
| 7 | Software Package 3 | Week 10–11 | Software version after Iteration 3 |
| 8 | Report 5 – Test Report | Week 11 | Software testing results |
| 9 | Full Software Package | Week 13 | Complete software package after testing and bug fixing |
| 10 | Report 6 – User Guide | Week 14 | User guide for the system |
| 11 | Report 7 – Final Project Report | Week 14 | Final project documentation |

## 4. Responsibility Assignments

RACI Chart: R~Responsible, A~Accountable, C~Consulted, I~Informed

| Responsibility | HungVDHE18 1369 | TuHAHE1821 11 | ThuNTMHE180 810 | AnNTHE1731 89 | LinhPMHE18 7215 |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | R,A | R | C | C | I |
| Project Introduction | A | C | R | I | C |
| Requirements Analysis & SRS | R,A | R | C | R | R |
| UI/UX Design | R | R | R,A | R | C |
| System Architecture Design | R,A | R | C | R | R |
| Database Design | R,A | R | R | R | C |
| Front-end Development | A | C | C | R | R |
| Back-end & API Development | R,A | R | R | C | C |
| AI Integration | R | R | C | R,A | C |
| System Integration | A,R | R | R | R | R |
| Integration Testing | R | A,R | C | R | R |
| System Testing & Bug Fixing | C | A,R | C | R | R |
| Deployment & Configuration | A,R | R | R | R | R |
| Project Documentation & Final Report | R | R | R,A | R | R |
| Final Presentation & Demo | A,R | R | R | R | R |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Team Meeting | All members | Discuss project progress, tasks, and problems | Weekly | Google Meet / Face-to- face |
| Task Progress Update | All members | Track task completion and assign new tasks | 2–3 times/ week | GitHub / Zalo |
| Document Sharing | All members | Share and update project documents | As needed | Google Drive / Google Docs |
| Code Review | All members | Review source code and identify technical problems | When code is updated | Google Meet/ GitHub |
| Project Review | All members | Review project status and prepare deliverables | End of each stage | Google Meet / Face-to- face |

## 6. Configuration Management

### 6.1 Document Management

Management Tools:

- Google Drive

- Google Docs

- Google Sheets

- GitHub

### The team uses Google Drive to store and manage project documents such as the Project Introduction, SRS, design documents, testing documents, reports, and presentation slides.

### Google Docs and Google Sheets are used for collaborative editing and updating project information. GitHub is also used to store and manage technical documents related to the project, helping the team track changes and maintain document versions.

### The Project Manager is responsible for monitoring progress, consolidating documents, and reviewing the final versions before submission to the mentor.

### 6.2 Source Code Management

Management Tools:

- GitHub

The team uses GitHub to manage and store the project source code, including the Front-end, Back-end, API, Database, and AI integration components.

Each team member works on a separate branch corresponding to their assigned tasks, then commits and pushes the code to the repository. Once a feature is completed, the code is reviewed and merged into the main branch to ensure system stability.

The Project Manager is responsible for monitoring the repository, managing source code integration, and preparing a stable version for testing, deployment, and demonstration.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Java/SpringBoot (BackEnd), React (Frontend) |
| Database | MySQL |
| IDEs/Editors | Visual Studio Code, IntelliJ |
| Diagramming | DrawIO, Figma, Visual Paragram |
| Documentation | Ms Office, Google Docs/Sheets |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Vercel(Front-end), Railway(Back-end, MySQL) |
| Project management | Jira(Schedule, Tasks, Defects) |
| Test tools | Postman |